## Cover
100-Day AI Governance Plan
For PE Portfolio Companies · Powered by SureCloud
How to use this workbook
1. 100-Day Planner — Your master action plan. Assign owners, set target dates, and track status for all 100-day activities.
2. AI Usage Map — Inventory every AI tool in use — sanctioned and shadow. Classify data risk and assign a review action.
3. Use-Case Register — Log potential AI use cases by function. Prioritise by measurable impact and track through to pilot launch.
4. Governance Assessment — Score your current AI governance maturity across the five dimensions: Discover, Classify, Control, Monitor, Evidence.
5. Board Report — The six questions every board pack should answer on AI. Complete quarterly and share with your investors.
Prepared by: Date:

## 100-Day Planner
100-Day AI Governance Planner
# | Action | Output / Definition of Done | Phase | Target Date | Completed | Status | Owner | Notes
PHASE 1 — MONTH 1 (Days 1–30)
1 | Appoint an AI accountability lead | Named executive with board-visible mandate, written terms of reference | Month 1 |  |  | Not started
2 | Run an AI governance assessment | Documented inventory of sanctioned tools, shadow AI, data classes, high-risk workflows, and current decision points | Month 1 |  |  | Not started
3 | Map AI usage across the organisation | Completed AI Usage Map tab with all tools, data flows, and shadow AI instances logged | Month 1 |  |  | Not started
4 | Identify and brief key function leads | All department heads engaged; each able to list top repetitive and judgment-heavy tasks | Month 1 |  |  | Not started
PHASE 2 — MONTHS 2–3 (Days 31–75)
5 | Build the use-case register | Completed Use-Case Register tab with use cases classified, impact scored, and owner assigned | Month 2–3 |  |  | Not started
6 | Select 3–5 priority pilots | Pilots chosen against measurable EBITDA, growth, retention, compliance, or risk reduction criteria | Month 2–3 |  |  | Not started
7 | Establish governance controls for pilot use cases | Approval workflows, human review requirements, and data handling policies in place before launch | Month 2–3 |  |  | Not started
8 | Standardise in one operating workspace | Central repository for prompts, process notes, owners, metrics, and approvals live and in use | Month 2–3 |  |  | Not started
9 | Launch pilots with defined success metrics | Each pilot has a named owner, baseline measurement, and 60-day review milestone | Month 2–3 |  |  | Not started
PHASE 3 — QUARTER 1 CLOSE (Days 76–100)
10 | Review pilot results against success metrics | Quantified outcomes for each pilot; go/no-go decision documented | Q1 |  |  | Not started
11 | Scale governed pilots into operating model | At least one pilot promoted into standard workflow with documented owner, review cadence, and human oversight point | Q1 |  |  | Not started
12 | Complete Governance Assessment (Sheet 4) | Maturity scores completed; gaps and improvement actions logged | Q1 |  |  | Not started
13 | Publish first Board Report (Sheet 5) | All six board questions answered; shared with investors | Q1 |  |  | Not started
14 | Establish monthly AI board reporting cadence | Recurring slot in board pack; template owner named; first three months scheduled | Q1 |  |  | Not started

## AI Usage Map
AI Usage Map — Sanctioned & Shadow AI Inventory
Complete one row per AI tool or use case. Include all consumer tools (ChatGPT, Copilot, Claude, Gemini etc.) used by any employee, even if unsanctioned.
Tool / Platform | Function / Use Case | Department(s) | Data Types Accessed | Sanctioned or Shadow | EU AI Act Risk Tier | Action Required | Owner | Notes
ChatGPT / GPT-4 | Email drafting, research summaries | Sales, Marketing | Customer names, deal context | Shadow — unmanaged | Limited | Issue usage policy; migrate to managed tenant
Microsoft Copilot | Meeting summaries, document drafting | All functions | Internal documents, emails, calendar data | Sanctioned | Minimal | Confirm data residency settings
[Add tool]
[Add tool]
[Add tool]

## Use-Case Register
AI Use-Case Register
Each function head: list your most repetitive, judgment-heavy, and customer-facing tasks. Score measurable impact against: EBITDA improvement · Revenue velocity · Risk reduction · Retention · Compliance
# | Use Case Description | Function / Department | Task Type | Measurable Impact Area | Estimated Impact | Automation Complexity | Owner | Status | Pilot Target Date | Notes
1 | Automate sales proposal first draft using account data | Sales | Repetitive / automatable | Revenue velocity | 30% reduction in proposal cycle time | Low — quick win |  | Idea
2 | Automated regulatory obligation monitoring across PortCo policies | Compliance | Judgment-heavy | Risk reduction | 60–70% reduction in manual audit effort | Medium — workflow redesign |  | Idea
3 | Board pack KPI extraction and standardisation | Finance | Repetitive / automatable | EBITDA improvement | 5 days → 4 hours board pack prep | Low — quick win |  | Idea
4 | [Add use case]
5 | [Add use case]

## Governance Assessment
AI Governance Assessment — Maturity Scorecard
1 = Not in place |  | 2 = Partially in place |  | 3 = Fully in place
Dimension | Assessment Question | Score (1–3) | Evidence / Current State | Gap / Action Required | Owner | Notes
DISCOVER
DISCOVER | Do you have a complete inventory of AI tools in use across the business?
DISCOVER | Have you identified and mapped shadow AI (consumer tools used without approval)?
DISCOVER | Are data flows from AI tools to external services documented?
DISCOVER | Are high-risk AI-influenced decision points identified?
CLASSIFY
CLASSIFY | Are AI use cases risk-tiered using a consistent framework (e.g. EU AI Act categories)?
CLASSIFY | Is there a documented definition of what constitutes a 'high-risk' AI use case for this business?
CLASSIFY | Are high-risk use cases treated differently in your governance process?
CONTROL
CONTROL | Are approval workflows in place before AI use cases go live?
CONTROL | Are human review requirements defined for AI-generated outputs in critical workflows?
CONTROL | Is there a third-party AI vendor due diligence process?
CONTROL | Are acceptable use policies communicated to all employees?
CONTROL | Are there data handling rules for what information can be passed into AI tools?
MONITOR
MONITOR | Are deployed AI use cases actively monitored for performance and accuracy drift?
MONITOR | Is there a process for reporting and investigating AI incidents or anomalies?
MONITOR | Are model and data changes tracked and their impact assessed?
MONITOR | Is there a regular (at least quarterly) review of the AI inventory?
EVIDENCE
EVIDENCE | Are AI-related controls, approvals, and reviews documented in an auditable log?
EVIDENCE | Could you produce evidence of AI governance maturity to a buyer in a diligence process today?
EVIDENCE | Are AI risk items included in your regular risk register and board reporting?
OVERALL SCORE |  |  | 1.0–1.5 = Significant gaps · 1.6–2.4 = Developing · 2.5–3.0 = Strong

## Board Report
AI Board Report — Six Questions for Every Board Pack
Complete this section before each board meeting. If management cannot answer these questions cleanly, the AI programme is moving faster than governance.
Company / PortCo: |  |  |  | Report Period:
# | Board Question | Management Response | Supporting Evidence | RAG Status | Last Updated
1 | Where is AI creating measurable value today? | Name specific use cases with quantified outcomes (not 'we are exploring AI'). |  | Not yet assessed
2 | Which use cases are high risk, and who signed them off? | List all high-risk AI decisions (hiring, credit, safety, compliance). Name the approving executive. |  | Not yet assessed
3 | What shadow AI did we find this quarter? | Report active discovery findings. 'None found' is only acceptable if discovery was actively run. |  | Not yet assessed
4 | What third parties, models, and data sources do we depend on? | List critical AI vendors, which models are used, and what data each accesses. |  | Not yet assessed
5 | What incidents, drift, or exceptions occurred? | Report all AI-related incidents, anomalies, or control exceptions — even minor ones. |  | Not yet assessed
6 | What evidence could we show a buyer tomorrow? | Confirm auditable records exist for all governed AI use cases. State what would take time to produce. |  | Not yet assessed
"If management cannot answer these cleanly, the AI programme is moving faster than governance - and that is a risk to your multiple." - SureCloud, AI Governance for PE